## TestingIssues
Sl # | Module | Page | Issue | Status | Testing Date
1 | Job Portal | Registration | Please assign right city to appropriate state. | Fixing | 2013-11-12
2 | Job Portal | Profile | Please correct the message "Click Here to List of Schools Based on Qualification". | Fixing | 2013-11-12
3 | Job Portal | Profile | No option to select or apply to any of the listed schools. | Fixing | 2013-11-12
4 | School Registration | PSTTI Home | Please correct the spelling of Regiestration. | Fixing | 2013-11-12
5 | School Registration | School Details | Error message for not entering land line is showing same as that of mobile. | Fixing | 2013-11-12
6 | School Registration | Vacancies | Please correct the message "Click Here List of Candidates Based on Job". | Fixing | 2013-11-12
7 | All | All | Please mark the mandatory fields with (*). | Fixing | 2013-11-12
8 | All | All | Please change the error message (The page at criticice.com says:) in alert box to proper error message. | Fixing | 2013-11-12
PSTTI.COM
1 | Job seekers | Registration | Please correct the message "Please give minimum 6 characters..!" in password ("password must be 6 characters..!") | Fixing | 13/12/2013
2 | Job seekers | Registration | mobile no validation is not done | Fixing | 13/12/2013
3 | Job seekers | Registration | Job As/Position Looking For as well as Graduates text field’s make it as compulsory | Fixing | 13/12/2013
4 | Job seekers | Edit | After editing Title as well as Experience fields are not displying all options | Fixing | 13/12/2013
5 | Job seekers | Registration | After emailid already exist mess its not redirecting to same page its going to login page | Fixing | 13/12/2013
7 | School Registration | School Details | Please correct the message "please enter the princepal name" in place of contact person name | Fixing | 13/12/2013
8 | School Registration | School Details | Please correct the message "please enter the mobile no" in place of land line no | Fixing | 13/12/2013
9 | School Registration | School Details | mobile as well as land line no validation is not done | Fixing | 13/12/2013
10 | School Registration | School Details | error messes are not in sequence | Fixing | 13/12/2013
11 | School Registration | School Details | Please correct the message "Please give minimum 6 characters..!" in password ("password must be 6 characters..!") | Fixing | 13/12/2013
12 | School Registration | School Details | error messes are not displying for re-password, as well as its redirecting to the login page | Fixing | 13/12/2013
13 | School Registration | Image uploads | More then one images we are not able to uploads | Fixing | 13/12/2013
14 | School Registration | school registration | we cant able to find currently we are in which page Ex:gallery,Vacancies | Fixing | 13/12/2013
15 | School Search | parent details | Please check on focus | Fixing | 13/12/2013
|  |  |  | Fixing | 13/12/2013

## CRM_ISSUES
Sl # | Module | Page | Issue | comments | Status | Testing Date | Fixed Date
1 | PTC | Client | mobile no validation is not done | resolved | Closed | 2013-11-11 | 2013-11-11
2 | PTC | Client | for empty Contact Person Position ,Error is going to displaying as well as its generate PTC-ID | Not need. | Closed | 2013-11-11 | 2013-11-11
3 | PTC | Client | Contact Person Mail-ID is mandatery | its mandatory because another one is company mail id | Closed | 2013-11-11 | 2013-11-11
4 | PTC | Client | Please mark the mandatory fields with (*). | I will discuss with manju sir on that issue. | Fixing | 2013-11-11 | 2013-11-11
5 | PTC | Lead | Without taking Product Type and Product Sub-Type It should not generate Lead-ID | resolved | Closed | 2013-11-11 | 2013-11-11
6 | PTC | Lead summary | Columns arrengements are not properly | fixed | Fixing | 2013-11-11 | 2013-11-11
7 | Lead summary | Lead-ID | Edit as well as delete buttons are not there | not needed | Closed | 2013-11-11 | 2013-11-11
8 | Lead | Lead | Columns arrengements are not properly | Fixing | Fixing | 2013-11-11 | 2013-11-11
9 | Lead | Lead-ID | Company Name, Product Type and Product Sub Type these all should comes in a single line | fixed | Closed | 2013-11-11 | 2013-11-11
10 | Client | Client | Delete button is not there | not needed | Closed | 2013-11-11 | 2013-11-11
11 | Client | Client | Contact Person Name, it should not take numbers | resolved | Closed | 2013-11-11 | 2013-11-11
12 | Client | Client | Something is visibe orange color letters above the Company name | resolved | Closed | 2013-11-11 | 2013-11-11
2nd Round Testing
SI # | Module | Page | Issue | comments | Status | Testing Date | Fixed Date
13 | PTC | Company name | Change the message as 'please enter Company name' | Fixed | Closed | 19-11-2013
14 | PTC | Address | Company Address field color is not changing into pink | Fixed | Closed | 19-11-2013
15 | PTC | Mail | Change the message as 'please enter mail-ID' when its blank | Fixed | Closed | 19-11-2013
16 | PTC | Phone No | After entering 10 digit no's then also we should not get a message | Fixed | Closed | 19-11-2013
17 | PTC | Contact Person Number | when this field is blank we should not get a message like 'Please enter correct phone no' | Fixed | Closed | 19-11-2013
18 | PTC | Client | Error messages should be in a sequence manner | Fixed | Fixed | 19-11-2013
19 | PTC | Contact Person Name | Contact Person Name should not allow the numbers | Not an issue |  | 19-11-2013
20 | PTC | Client | After showing error message it should wait until we pass the values as well as it should not create ID | Fixed | Closed | 19-11-2013
21 | PTC | Client | Table arrangement is not proper | Fixed | Fixing | 19-11-2013
22 | PTC | Lead states | Hide button is not working | Fixed | Closed | 19-11-2013
23 | PTC | Lead states | need space bettween Lead bar and Company information | Not an issue | Closed | 19-11-2013
24 | PTC | Lead states | updated commends are not dispalying in bellowed table | Fixed | Closed | 19-11-2013
25 | PTC | User | extra check boxes should not occure | Fixed | Not an issue | 19-11-2013
26 | PTC | User | In table, Products values are ending with single comma is enough | Fixed | Not an issue | 19-11-2013
27 | PTC | User | Role option must be mandatory fields, check it ones | Fixed | Fixing | 19-11-2013
28 | PTC | Client | Delete buttons are not there | Not needed | Closed | 19-11-2013
3nd Round Testing
Sl # | Module | Page | Issue | comments | Status | Testing Date | Fixed Date
29 | PTC | Address | Should not accept space or it should take only characters | fixed | Closed | 2013-11-20
30 | PTC | Phone no's | phone no's should not accepts alphabets | fixed | Re-Open | 2013-11-20
31 | PTC | Address | Area of the address, css is not maching to the other fields | fixing | Closed | 2013-11-20
32 | PTC | Lead management | Cant able to see full table of the lead management | fixed | Closed | 2013-11-20
33 | PTC | Lead states | Edit n delete or like buttens are not there | not needed | Closed | 2013-11-20
34 | PTC | Lead states | In between reference and its name space should not be there | fixed | Closed | 2013-11-20
35 | PTC | Lead states | When we are in lead states page, color of lead summery button must be change, to know currenly we are in that page | Fixing | Fixing | 2013-11-20 |  | previous comments needed
36 | PTC | Lead states | Before the update, Follw Up-Date n Status are coming inside the table | needed | Closed | 2013-11-20 |  | product name and sub product name are inserted same
37 | PTC | Master | Instead of product names it shoud be sub-product names | needed | Closed | 2013-11-20
38 | PTC | Master | If we deleted in between of the product names si.no should change along with the serial no's | Fixing | Fixing | 2013-11-20
39 | PTC | Lead management | Lead Description should not accept space | fixed | Closed | 2013-11-20
40 | PTC | Lead management | Table is not visible properly | fixed | Closed | 2013-11-20
41 | PTC | User | In between product space should be equal | not needed | Fixing | 2013-11-20
42 | PTC | User | Table is not visible properly | fixed | Closed | 2013-11-20
43 | PTC | Master | Space should not accept in product and sub-product | fixing | Fixing | 2013-11-20
44 | PTC | All | For all tables scrollbar must be there | fixed | Closed | 2013-11-20
45 | PTC | All | Before deleting anything from table ones conformation mess is required | fixed | Closed | 2013-11-20
46 | PTC | All | After deleting mess is required | fixed | Re-OPen | 2013-11-20
4th round testing
Sl # | Module | Page | Issue | comments | Status | Testing Date | Column8
1 | Client | Client | While Updating, Clint name already exist error message is coming | Fixing | Open | 2013-12-05
2 | Client | Company name | Change the message as 'please enter Company name' | Fixing | Open | 2013-12-05
3 | Lead | Lead | Editing option is not working for "Assigned To" | Fixing | Open | 2013-12-05
4 | Lead | Lead Summary | Status and Product are combined or merged | Fixing | Open | 2013-12-05
5 | Lead | Lead Summary | Assignee:Manjunath,Status:No States,Product:Zeboba, Start Date:2/12/2013 end date:2/12/2013, still output is showing on 5/12/2013 it should not happen. | Fixing | Open | 2013-12-05
6 | Lead | Lead Summery | Assignee:rajesh, States:Closed/lost,Product:Z,but in table Assignee:shanker is coming, it should not happen | Fixing | Open | 2013-12-05
7 | Lead | Lead Summery | By selecting Product, automaticali sub-product of that product list must display | Fixing | Open | 2013-12-05
8 | Lead | Lead Summery | Based on Assignee, States Should disply | Fixing | Open | 2013-12-05
9 | Lead | Lead Status | After entering Comment also its showing error message, it should not happen | Fixing | Open | 2013-12-05
10 | Lead | Lead Status | After entering comment PTCID-009 or Hide button(that dable is displaying above the Lead bar ) | Fixing | Open | 2013-12-05
11 | Lead | Lead Summery | As Product type column is present, like status column is there means its good to identify | Fixing | Open | 2013-12-05
12 | Lead | Lead management | After deleting, message will comes but if I canceled also its going to deleted | Fixing | Open | 2013-12-05
13 | Lead | Lead Summery | In lead module should not contain task bars or task summary bars | Fixing | Open | 2013-12-05
14 | Task | Task management | tab is not moving proper | Fixing | Open | 2013-12-05
15 | Task | Leads | by default leads should be select option | Fixing | Open | 2013-12-06
16 | Task | Task management | Table is not based on any order(it should be based on Lead-Id or Date) | Fixing | Open | 2013-12-06
17 | Task | Task Status | Task status table is showing above the task bar after giving the comment | Fixing | Open | 2013-12-06
18 | Task | Status | Status table is not working | Fixing | Open | 2013-12-06
19 | Task | Task Status | Error messages are not showing for Discription and all | Fixing | Open | 2013-12-06
20 | Task | Task Summery | In Status table no. of items are not going to change | Fixing | Open | 2013-12-06
21 | Task | Task Status | Status table is not required itseems | Fixing | Open | 2013-12-06

## CRM_LEAD
Sl # | Module | Sub-Module | Tab/Field | Issues | Comments | Status | Working | Testing Date | Fixing Date | Comments2 | Column1
1 | Lead | Lead Management | Table(Lead Description) | Description should be with in the column | Fixing | Open |  | 2013-12-19
2 | Lead | Lead Management | Edit and Delete buttons | Edit' and 'Delete' button should be in same line, when description is lengthy | Fixing | Open |  | 2013-12-19
3 | Lead | Lead Management | Delete Button(cancel) | In delete button, 'CANCEL' button also work as 'OK' button | Fixing | Re-Open |  | 2013-12-19
4 | Lead | Lead Management | Assigned to | Rajesh and Prathik names are not displaying in the lead table | Fixed | Closed |  | 2013-12-19 | 2013-12-20
5 | Lead | Lead Management | Table(Coloumns name) | When Lead description are lengthy the allignment of columns names are not correct | Fixing | Open |  | 2013-12-19
6 | Lead | Lead Management
7 | Lead | Lead Summary | Table | Table is not displaying fully as well as scrol bar is also not present | Fixing | Open |  | 2013-12-19
8 | Lead | Lead Status | Comment | After entering comment also Error message is displaying | Fixing | Open |  | 2013-12-19
9 | Lead | Lead Status | Comment | In comment fields some of the options are not working | Fixing | Open |  | 2013-12-19
10 | Lead | Lead Status | Update | After updating, entered field should become blank | Fixing | Open |  | 2013-12-19
11 | Lead | Lead Status | Lead Id table | After pressing navigation buttons Lead id Table is not working(Hide) | Fixed | Closed |  | 2013-12-19
12 | Lead | Lead Status | Assignee table | In Assignee table Prathik link is not working (no leads found message is not displaying) | Fixing | Open |  | 2013-12-19
13 | Lead | Lead Status | Filter | Sub-Product should display based on product selected | Fixed | Closed |  | 2013-12-19
14 | Lead | Lead Status | Filter | Start Date and End Date Should not accept future dates | Fixing | Open |  | 2013-12-19
15 | Lead | Lead Status | Filter | Status Option should take (Consider) only present status | Fixing | Open |  | 2013-12-19
16 | Lead | Lead Status | Lead Summary | Side tables width should be same | Fixing | Open |  | 2013-12-19
17 | Lead | All | NA | CSS of Lead module should be same after entered into the Lead summary/lead status | Fixing | Open |  | 2013-12-19
18 | Lead | Lead Status | Below Comment field | Status field make it as mandatory field(B'case either its moving 'no status' or 'others') | Not an Issue | Closed |  | 2013-12-19
19 | Lead | Lead Summary | Lead Summary of all Status Table | Status coloumn should be there | Fixed | Closed |  | 2013-12-19
20 | Lead | Lead Summary | Filter | Client field should be present | Fixed | Closed |  | 2013-12-19
21 | Lead | Lead Status | Lead Status Table | Name of the Product and Sub-product should include in the table | Fixed | Closed |  | 2013-12-19
2nd Rount Testing
22 | Lead | NA | Lead Management(All) | Make All fields are mandatory(*) | Fixed | Open |  | 2013-12-19
23 | Lead | NA | Lead-ID | without selecting any product or assignee, lead id is submitted but not listing in the lead table | Fixed | Open |  | 2013-12-19
24 | Lead | NA | Lead-ID | After deleting row,After one lead submistion, Lead-ID is automaticaly incrementing | Fixing | Open |  | 2013-12-19
25
26 | Lead | NA | Navgation buttons | Navigation buttons are not working correctly | Fixing | Open |  | 2013-12-19
27 | Lead | NA | Resolution | Page is not fit to the screen | Fixing | Open |  | 2013-12-19
28 | Lead | Lead Summary | Scroll bar | Scroll bar button is not working correctly | Fixing | Open |  | 2013-12-19
29 | Lead | Lead Summary | Filter (Client id) | For particular client ID , some of the lead ID's are not present in the status table | Fixed | Open |  | 2013-12-19
30 | Lead | Lead Status | Status | If Status is open, it should display as 'open' in Stauts coloumn | Fixed | Open |  | 2013-12-19
31 | Lead | Lead Status | Table | Without follow-up-date,status,amount,quantity. Comment statement is updated | Fixed | Open |  | 2013-12-19
32 | Lead | Lead Status | Amount | Amount should display error message, if we entered characters | Fixed | Open |  | 2013-12-19
33 | Lead | Lead Status | No of quantities | It should not take characters, it should display error message | Fixed | Open |  | 2013-12-19
34
1 | Lead | NA | Client Name | This field is working fine |  |  | TRUE | 24/12/2013
2 | Lead | NA | Lead Description | This field is working fine |  |  | 2 | 24/12/2013
3 | Lead | NA | Product Type | This field is working fine |  |  | 3 | 24/12/2013
4 | Lead | NA | Sub-Product | This field is working fine |  |  | 4 | 24/12/2013
5 | Lead | NA | Assigned to | This field is working fine |  |  | 5 | 24/12/2013
6 | Lead | NA | submit | This Button is working fine |  |  | 6 | 24/12/2013
7 | Lead | NA | Edit | This Button is working fine |  |  | 7 | 24/12/2013
8 | Lead | NA | Edit | After editing Lead-ID should display on table | Fixing | Open | FALSE | 24/12/2013
9 | Lead | NA | Update | This Button is not working fine(update button is not working) | Fixing | Open | FALSE | 24/12/2013
10 | Lead | NA | Delete | This Button is working fine |  |  | 7 | 24/12/2013
11 | Lead | Delete | Cancel | This Button is working fine |  |  | 7 | 24/12/2013
12 | Lead | Delete | OK | This Button is working fine |  |  | 7 | 24/12/2013
13 | Lead | NA | Navigation Buttons | After pressing Navigation buttons, In Status table 'ALL' and 'No Status' links are not working | Fixing | Open | FALSE | 24/12/2013
14 | Lead | Lead Summary | Status table | Status table, In this all links are working fine |  |  | TRUE | 24/12/2013
15 | Lead | Lead Summary | Product Table | Product table, In this all links are working fine |  |  | TRUE | 24/12/2013
16 | Lead | Lead Summary | Product closed table | Product closed table, In this all links are working fine | ` |  | TRUE | 24/12/2013
17 | Lead | Lead Summary | Lead Status Table | This table is working fine |  |  | TRUE | 24/12/2013
18 | Lead | Lead Summary | Scroll bar | Scroll bar is not compatible with other OS | Fixing | Open | FALSE | 24/12/2013
19 | Lead | Lead Summary | Navigation Buttons | Page Navigation buttons are not working correctly | Fixing | Open | FALSE | 24/12/2013
20 | Lead | Filter | Client | This field is not showing the client options in drop down box (OS) | Fixing | Open | FALSE | 24/12/2013
21 | Lead | Filter | Assignee | Based on 'Assignee' table is displaying |  |  | TRUE | 24/12/2013
22 | Lead | Filter | Status | Based on 'Status' table is displaying |  |  | 2 | 24/12/2013
23 | Lead | Filter | Product | Based on 'Product' table is displaying |  |  | 3 | 24/12/2013
24 | Lead | Filter | Sub-Product | This field is working fine |  |  | 4 | 24/12/2013
25 | Lead | Filter | Start Date | Based on 'Start Date' table is displaying |  |  | 5 | 24/12/2013
26 | Lead | Filter | End Date | Based on 'End Date' table is displaying |  |  | 6 | 24/12/2013
27 | Lead | Filter | Follow-up-date | This field is not working fine(in this we cant able to select future years ) | Fixing | Open | 7 | 24/12/2013
28 | Lead | Filter | Search | This Button is working fine |  |  | 8 | 24/12/2013
29 | Lead | Lead Status | PTCID button | This Button is working fine |  |  | 9 | 24/12/2013
30 | Lead | Lead Status | Hide | This Button is working fine |  |  | 10 | 24/12/2013
31 | Lead | Lead Status | Comment | This field is working fine |  |  | 11 | 24/12/2013
32 | Lead | Lead Status | Follow-up-date | This field is working fine(but it should not be empty) |  |  | 12 | 24/12/2013
33 | Lead | Lead Status | Status | This field is working fine(but it should not be empty) |  |  | 13 | 24/12/2013
34 | Lead | Lead Status | Amount | In this field not accepting decimal values(but it should not be empty) | Fixing | Open | FALSE | 24/12/2013
35 | Lead | Lead Status | Tax | This field is working fine |  |  | 15 | 24/12/2013
36 | Lead | Lead Status | Total | It should not accept the 'Manually' values | Fixing | Open | FALSE | 24/12/2013
37 | Lead | Lead Status | No of quantities | (its not accepting characters)if it is empty field then it should display error message | Fixing | Open | FALSE | 24/12/2013
38 | Lead | Lead Status | Update | This Button is working fine |  |  | 18 | 24/12/2013
39 | Lead | Lead Status | Full Details | This Button is working fine |  |  | 19 | 24/12/2013
40 | Lead | Lead Status | Hide | This Button is working fine |  |  | 20 | 24/12/2013
41 | Lead | Lead Status |  | Make All fields are mandatory | Fixing | Open | FALSE | 24/12/2013
42 | Lead | NA | Navigation Buttons | After pressing Navigation buttons, In Status table 'ALL' and 'No Status' links are not working | Fixing | Open | FALSE | 24/12/2013
43 | Lead | Lead Status/Summary | Date | Date Picker(Icon or image) should be there | Fixing | Open | FALSE | 24/12/2013
44 | Lead | ALL | ALL | Make All fields are mandatory(*) | Fixing | Open | FALSE | 24/12/2013
45 | Lead | Lead Status | PTCID Table | Previous comments column is not present in Linux | Fixing | Open | FALSE | 24/12/2013
46 | Lead | Lead Status | Task Button | This Button is working fine(re directing into task page) |  |  | TRUE | 24/12/2013
47 | Lead | Lead Status | Task Summary | This Button is working fine(re directing into task page) |  |  | TRUE | 24/12/2013
48 | Lead | Lead Status | Lead Summary | This Button is working fine(re directing into task page) |  |  | TRUE | 24/12/2013
49 | Lead | Lead status | Product& Assignee Table | This field will become empty when we come back from Task and Task summary | Fixing | Open | FALSE | 24/12/2013
50 | Lead | Lead Summary | Product table | Geotracer link is not working(Linux) | Fixing | Open | FALSE | 24/12/2013
51 | Lead | Lead Summary | Status table(ALL) | Status table 'All' link is not working | Fixing | Open | FALSE | 24/12/2013

## CRM_TASK
Sl # | Module | Sub-Module | Tab/Field | Issues | Comments | Status | Working | Testing Date | Fixing Date | Comments2
1 | Task | NA | Task Summary | Position of the Task Summary Button should same as lead summary | Fixing | Open |  | 2013-12-20
2 | Task | NA | updated table | After updating the edited field, the updated fields are not listing in the task-id table | Fixing | Open |  | 2013-12-20
3 | Task | NA | Target Date | After updating Target Date should not accept past dates | Fixing | Open |  | 2013-12-20
4 | Task | NA | Submit | After updating Submit page should display | Fixed | Closed |  | 2013-12-20
5 | Task | NA | Update | After updating PTC-ID message is coming | Fixed | Closed |  | 2013-12-20
6 | Task | NA | Table | Alignment of the table is not correct | Fixed | Closed |  | 2013-12-20
7 | Task | NA | Leads | After editing Lead-ID should be displayed in task management such that we can easily identify the which lead is edited | Fixing | Open |  | 2013-12-20
8 | Task | NA | Description | For space line break(<br>) tags are displaying in table after submission | Fixing | Open |  | 2013-12-20
9 | Task | NA | Task table | Navigation button is not working correctly | Fixed | Open |  | 2013-12-20
10 | Task | Task Summary | Task Summary of all | There is no scroll bar to scroll the page | Fixing | Open |  | 2013-12-20
11 | Task | Task Summary | Task Summary of all | Navigation button is not working correctly(when we select any status field) | Fixed | Closed |  | 2013-12-20
12 | Task | Task Summary | Task status | After updating Task-ID table is displaying above the Task status bar | Fixing | Open |  | 2013-12-20
13 | Task | Task status | Description | Make Description field as mandatory | Fixed | Closed |  | 2013-12-20
1 | Task | NA | Description | This field is working fine |  |  | TRUE | 24/12/2013
2 | Task | NA | Target Date | Date should take only future dates | Fixed | Re-open | FALSE | 24/12/2013
3 | Task | NA | Target Date | Date picker image should be there | Fixed | Re-open | FALSE | 24/12/2013
4 | Task | NA | Assignee | This field is working fine |  |  | TRUE | 24/12/2013
5 | Task | NA | Lead | This field is working fine |  |  | TRUE | 24/12/2013
6 | Task | NA | Submit | This button also working fine |  |  | TRUE | 24/12/2013
7 | Task | NA | Edit | This button also working fine |  |  | TRUE | 24/12/2013
8 | Task | NA | Update | Update button is not working (all fields are not updating) | Fixed | Re-open | TRUE | 24/12/2013
9 | Task | NA | Task Summery | This button also working fine |  |  | TRUE | 24/12/2013
10 | Task | Task Summary | Status | In 'status table' All links are not working | Fixed | Re-open | FALSE | 24/12/2013
11 | Task | Task Summary | Task Assignee(no of task) | In 'Task Assignee table' All links are not working | Fixed | Re-open | FALSE | 24/12/2013
12 | Task | Task Summary | Task Assignee(Closed task) | In 'Task Assignee table' All links are not working | Fixed | Re-open | FALSE | 24/12/2013
13 | Task | Task Summary of all | Task Summary of all table | All links are working fine |  |  | TRUE | 24/12/2013
14 | Task | Task Status | Task Date | Task Date'' field is not fetching proper values | Fixed | Closed | TRUE | 24/12/2013
15 | Task | Task Status | Task Id | This field fetching proper value |  |  | TRUE | 24/12/2013
16 | Task | Task Status | Task Description | This field fetching proper value |  |  | 2 | 24/12/2013
17 | Task | Task Status | PTLID | This button also working fine |  |  | 3 | 24/12/2013
18 | Task | Task Status | Description | This field is working fine |  |  | 3 | 24/12/2013
19 | Task | Task Status | Target Date | Target Date' field is not fetching proper values | Fixed | Closed | TRUE | 24/12/2013
20 | Task | Task Status | Assignee | This field fetching proper value |  |  | TRUE | 24/12/2013
21 | Task | Task Status | Status | This field fetching proper value |  |  | TRUE | 24/12/2013
22 | Task | Task Status | Update | This button also working fine |  |  | TRUE | 24/12/2013
23 | Task | Task Status | Status | In 'status table' All links are not working | Fixed | Open | FALSE | 24/12/2013
24 | Task | Task Status | Task Assignee(no of task) | In 'Task Assignee table' All links are not working | Fixed | Open | FALSE | 24/12/2013
25 | Task | Task Status | Task Assignee(Closed task) | In 'Task Assignee table' All links are not working | Fixed | Open | FALSE | 24/12/2013
26 | Task | Task Status

## CRM_Finance
Sl # | Module | Sub-Module | Tab/Field | Issues | Comments | Status | Working | Testing Date | Fixing Date
1 | Finance | Financial Details | Details | Without any description Financial ID is submitted | Fixing | Open |  | 2013-12-21
2 | Finance | Financial Details | Date | More space between the Date and date input field | Fixing | Hold |  | 2013-12-21
3 | Finance | Financial Details | NA | After entering Details also its asking 'Enter Details' when submit is pressed | Fixing | Open |  | 2013-12-21
4 | Finance | Reports | NA | There is no footer scroll bar to see the table correctly | Fixing | Hold |  | 2013-12-21
5 | Finance | Reports | NA | Details description is not within the column its taking too lengthy | Fixing | Open |  | 2013-12-21
6 | Finance | Financial Details | Amount | Amount field is not accepting the decimal point. | Fixing | Open |  | 2013-12-21
7 | Finance | Financial Details | Date | After editing financial-ID, edited date is not displaying in the date field | Fixing | Open |  | 2013-12-21
8 | Finance | Financial Details | PTF-ID | After editing PTF-ID should display on top of the table. | Fixing | Open |  | 2013-12-21
9 | Finance | Financial Details | NA | Sub menus of the finance field should be highlighted | Fixing | Open |  | 2013-12-23
10 | Finance | New fields | NA | ALL, Inflow, Outflow fields should be there above the table | Fixing | Open |  | 2013-12-23
11 | Finance | Reports | NA | FROM DATE should be one month earlier date and TO DATE should present date as a default | Fixing | Open |  | 2013-12-23
1 | Finance | NA | Payment Details | We can select Inflow either Outflow, radio buttons are working fine |  |  | TRUE | 27/12/2013
2 | Finance | NA | Date | Date formate is not matching with other module | Fixing | Open | FALSE | 27/12/2013
3 | Finance | NA | Description | This option field is working fine |  |  | TRUE | 27/12/2013
4 | Finance | NA | Amount | Amount field is displaying more then one point value (ex:456.45.45.45.45) | Fixing | Open | FALSE | 27/12/2013
5 | Finance | NA | Made of payment | Made of payment option field is working fine |  |  | TRUE | 27/12/2013
6 | Finance | NA | Details of payment | Details of payment text field is working fine |  |  | TRUE | 27/12/2013
7 | Finance | NA | Details | Details text field is working fine |  |  | TRUE | 27/12/2013
8 | Finance | NA | Submit | Submit button is working fine |  |  | TRUE | 27/12/2013
9 | Finance | NA | inflow/outflow | Inflow and Outflow font size should be differ from table attributes | Fixing | Open | FALSE | 27/12/2013
| Finance | NA | Tables | Maximum 10 rows inflow and 10 rows outflow should present |  |  | TRUE | 27/12/2013
| Finance | NA | Full Details | Full Details button is working fine |  |  | TRUE | 27/12/2013
10 | Finance | Financial Details | NA | Finance button should highlight after entering into the finance details page | Fixing | Open | FALSE | 27/12/2013
11 | Finance | Financial Details | Edit | Edit button is working fine |  |  | TRUE | 27/12/2013
12 | Finance | Financial Details | Edit | After editing PTF-ID should display on top of the table.(You are Editing PTFID-00033 ) | Fixing | Open | FALSE | 27/12/2013
13 | Finance | Financial Details | Date | Date image/icon should be present after the date field | Fixing | Open | FALSE | 27/12/2013
14 | Finance | Financial Details | Date | We cant able to change/alter the date |  |  | TRUE | 27/12/2013
15 | Finance | Financial Details | Details | Details text field make it as mandatory | Fixing | Open | FALSE | 27/12/2013
|  | Financial Details | Update | Update button is working fine |  |  | TRUE | 27/12/2013
16 | Finance | Financial Details | All | All button is working fine but change the CSS of 'ALL' button | Fixing | Open | FALSE | 27/12/2013
17 | Finance | Financial Details | Inflow | Inflow button is working fine but change the CSS of 'Inflow' button | Fixing | Open | FALSE | 27/12/2013
18 | Finance | Financial Details | Outflow | Outflow button is working fine but change the CSS of 'Outflow' button | Fixing | Open | FALSE | 27/12/2013
19 | Finance | Financial Details | Navigation buttons | Navigation buttons are working fine |  |  | TRUE | 27/12/2013
20 | Finance | Financial Details | inflow/outflow | After pressing inflow button all inflow(payment Details) are displaying, but after editing also it should present in same page, But should not navigate to all(payment Details) | Fixing | Open | FALSE | 27/12/2013
21 | Finance | Financial Details | Outflow | After pressing outflow button all outflow(payment Details) are displaying and navigation buttons are displaying, if we press navigation buttons its navigate to all(payment Details) | Fixing | Open | FALSE | 27/12/2013
| Finance | NA | Reports | Reports button is working fine |  |  | TRUE | 27/12/2013
23 | Finance | Reports | NA | Finance button should highlight after entering into the finance details page | Fixing | Open | FALSE | 27/12/2013
24 | Finance | Reports | Payment Details | Paymentdetails option field is working fine |  |  | TRUE | 27/12/2013
25 | Finance | Reports | Description | Description option field is working fine |  |  | TRUE | 27/12/2013
26 | Finance | Reports | Mode of Payment | Modeofpayment option field is working fine |  |  | TRUE | 27/12/2013
27 | Finance | Reports | From/To Date | FROM DATE should be one month earlier date and TO DATE should present date as a default | Fixing | Open | FALSE | 27/12/2013
28 | Finance | Reports | Submit | Submit button is working fine |  |  | TRUE | 27/12/2013
29 | Finance | Reports | Table | table should display below the Reports table, its not displaying fully | Fixing | Open | FALSE | 27/12/2013
30 | Finance | Reports | Payment Details | Paymentdetails change into 'PaymentDetails' | Fixing | Open | FALSE | 27/12/2013
31 | Finance | All | All | After showing error message,focus should go back to that respective place | Fixing | Open | FALSE | 27/12/2013
32 | Finance
33 | Finance
34 | Finance
35 | Finance
36 | Finance
37 | Finance
38 | Finance
39 | Finance
40 | Finance
41 | Finance
42 | Finance
43 | Finance
44 | Finance
45 | Finance
46
47
48

## CRM_Inventory
Sl # | Module | Sub-Module | Tab/Field | Issues | Comments | Status | Working | Testing Date | Fixing Date
1 | Inventory | Item Summary | NA | Names should be mentioned for particular Table such as Product,Vendor tables | Fixing | Open |  | 2013-12-21
2 | Inventory | PTI-ID | NA | After editing PTI-ID should display above the table | Fixing | Open |  | 2013-12-21
3 | Inventory | ADD ITEM | NA | ADD ITEM should be mentioned in sub menus | Fixing | Open |  | 2013-12-21
1 | Inventory | NA | Item Name | ItemName text field is working fine |  |  | TRUE | 27/12/2013
2 | Inventory | NA | RackNo | RackNo text field is working fine |  |  | 2 | 27/12/2013
3 | Inventory | NA | PartNo | PartNo text field is working fine |  |  | 3 | 27/12/2013
4 | Inventory | NA | CompanyName | CompanyName option field is working fine |  |  | 4 | 27/12/2013
5 | Inventory | NA | ItemSpecification | ItemSpecification text field is working fine |  |  | 5 | 27/12/2013
6 | Inventory | NA | Product | Product options are working fine |  |  | 6 | 27/12/2013
7 | Inventory | NA | Vendor | Vendor options are working fine |  |  | 7 | 27/12/2013
8 | Inventory | NA | Submit | Submit button is working fine |  |  | 8 | 27/12/2013
9 | Inventory | NA | Tab | Tab button is working fine |  |  | 9 | 27/12/2013
10 | Inventory | NA | Edit | After editing PTI-ID should display on top of the table.(You are Editing PTIID-00033 ) | Fixing | Open | FALSE | 27/12/2013
11 | Inventory | NA | Update | Update button is working fine |  |  | TRUE | 27/12/2013
12 | Inventory | NA | Update | ItemSpecification text field is working fine,but make it as mandatory field | Fixing | Open | FALSE | 27/12/2013
13 | Inventory | NA | AddItem | AddItem button is working fine, but here there is no use of this button | Fixing | Open | FALSE | 27/12/2013
14 | Inventory | NA | ItemSummary | ItemSummary button is working fine |  |  | TRUE | 27/12/2013
15 | Inventory | ItemSummary | Product | Product table is working fine |  |  | TRUE | 27/12/2013
16 | Inventory | ItemSummary | Vendor | Vendor table is working fine(Vendor name should be unique) | Fixing | Open | FALSE | 27/12/2013
17 | Inventory | ItemSummary | CompanyName | Attribute of the table Companyname should be like 'CompanyName' |  |  | TRUE | 27/12/2013
18 | Inventory | ItemSummary | ItemSummary | ItemSummary button is not required in this page | Fixing | Open | FALSE | 27/12/2013
19 | Inventory | ItemSummary | Vendor button | Vendor button is working fine |  |  | TRUE | 27/12/2013
20 | Inventory | Vendor | Vendor | Vendor button is not required in this page | Fixing | Open | FALSE | 27/12/2013
21 | Inventory | Vendor | Vendor Name | this field is working fine |  |  | TRUE | 27/12/2013
22 | Inventory | Vendor | Phonenumber | this field is working fine |  |  | TRUE | 27/12/2013
23 | Inventory | Vendor | E-mail | Email text field is working fine |  |  | TRUE | 27/12/2013
24 | Inventory | Vendor | Category | Category option field is working fine |  |  | TRUE | 27/12/2013
25 | Inventory | Vendor | Edit | After editing PTV-ID should display on top of the table.(You are Editing PTVID-00033 ) | Fixing | Open | FALSE | 27/12/2013
26 | Inventory | Vendor | Edit | After editing Address and Description fields make it as mandatory fields | Fixing | Open | FALSE | 27/12/2013
27 | Inventory | Vendor | Update | Update button is working fine |  |  | TRUE | 27/12/2013
28 | Inventory | Vendor | Tables | Gap should be there in between two tables | Fixing | Open | FALSE | 27/12/2013
29 | Inventory | Vendor | Vendor Name | If we give big vendor name means, In Inventory Item table, position of the submit button is changing | Fixing | Open | FALSE | 27/12/2013
30 | Inventory | All | All | After showing error message,focus should go back to that respective place | Fixing | Open | FALSE | 27/12/2013

## CRM_Resource
Sl # | Module | Sub-Module | Tab/Field | Issues | Comments | Status | Testing Date | Fixing Date
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
1 | Resource | Resource Summary | Table | There is no need of the date field in the table | Fixing | Open | 2013-12-21
2 | Resource | Resource Summary | Submit button | Submit button should come downside the comment box. It is not the user friendly | Fixing | Open | 2013-12-21
3 | Resource | Resource Summary | NA | Names should be mentioned for particular Table such as Product,Sub-product tables | Fixing | Open | 2013-12-23
4 | Resource | Table | PTRID | After editing the PTR-ID should display above the table | Fixing | Open | 2013-12-23