## Chiramith
SL # | Main Module | SubModule | Assigned To | Status | Start Date Time | End Date Time(Completed) | Comments | Status | Modules
1 | Dashboard | [6 empty] | Working | 3
2 | Master | User | Dillibabu | Completed | 2014-08-03 | 2014-08-03 |  | Remaining | 2
3 | Master | Vendors | Guru | Completed | 2014-08-03 | 2014-10-03 |  | Completed | 13
4 | Master | RM Category | Guru | Completed | 2014-08-03 | 2014-10-03 |  | Total | 18
5 | Master | Product Category | Guru | Completed | 2014-10-03 | 2014-11-03
6 | Master | Raw Material | Karthik | Completed | 2014-08-03 | 2014-08-03
7 | Master | Assigned Material | Karthik | Completed | 2014-10-03 | 2014-11-03
8 | Master | Tax | Karthik | Completed | 15/03/2014 | 15/03/2014
9 | Master | Credit Period | Karthik | Working
10 | Stock Management | Invoice Details | Yuvasakthi | Completed | 2014-11-03 | 2014-11-03
11 | Stock Management | Stock Inventry | Yuvasakthi | Working | 2014-11-03
12 | Stock Management | Stock Status | Yuvasakthi | Working
13 | Issuance |  | Dillibabu | Completed | 2014-09-03 | 14/3/2014
14 | Product Management | Product | Guru | Completed | 2014-10-03 | 2014-10-03
15 | Product Management | Product BOM | Guru | Completed | 2014-11-03 | 2014-11-03
16 | Product Management | BOM Status | Guru | Working | 2014-11-03
17 | Kitting |  | Karthik | Completed | 2014-12-03 | 14/03/2014
18 | Login/logout |  | Dillibabu | Completed | 2014-08-03 | 2014-08-03